## Sheet1
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE QUARTER ENDING MARCH 31, 2020
Province of Davao del Norte
|  | Location | Total Cost |  | Date Started |  | Target | Project Status |  | No. of | Remarks
Program or | [6 empty] | Completion | % of | Total Cost | Extensions,
Project | [6 empty] | Date | Completion | Incurred to Date | if any
TRUST FUND
1. DOH-CENTER FOR HEALTH DEV'T.
1.2. Filariasis Elimination Grant |  | Province Wide |  | 1250000 |  |  |  | 95% | 1233102.83 |  | On going
2. PAMANA
2.1. Rehab.of San Jose Sitio Mahayahay,Magwawa FMR |  | Sto. Tomas |  | 15000000 |  | 2016-06-07 | 2017-01-04 | 98% | 13913318.99 |  | On going
2.3. Open.of Camansa-Sitio Bankawan-Binancian FMR |  | Asuncion |  | 20000000 |  | 2016-04-25 | 2017-01-11 | 95% | 19576395.89 |  | On going
2.4. Concreting/Impvt of FMR from Linayapan-Malapanit-Dangulog Ph2, Brgy Sto.Nino |  | Talaingod |  | 16050000 |  | 04/17/15 | 2016-01-15 | 95% | 16050000 |  | On going
2.5. Rehab/Impvt Prk 3 Palma Gil-Prk2 Tugas-Naseco FMR |  | Kapalong |  | 50500288.95 |  | 07/07/16 | 2019-04-14 | 100% | 48999412.68 |  | Completed as per physical accomplishment. Financial documents still on process | /
2.6. Const. of BIGA RCDG Bridges |  | Kapalong |  | 24959503.45 |  | 07/01/16 | 2020-03-25 | 85.37% | 20000000 |  | Suspended due to RROW | /
2.7. Opening/Impvt Mambing Brgy Cabidianan FMR |  | New Corella |  | 10000000 |  | 2016-03-15 | 2016-09-02 | 95% | 9328117.06 |  | On going
2.8.Construction of Food Grade Banana Flour Production Facility |  | Panabo City |  | 3000000 |  | 2017-07-03 | 2017-09-23 | 100% | 3000000 |  | COMPLETED
2.9. Construction of Civic Center, Madaum |  | Tagum City |  | 3000000 |  | 2018-01-28 | 2018-09-24 | 100% | 2913872.98 |  | Completed as per physical accomplishment. Financial documents still on process
2.10. Construction of Civic Center, San Isidro |  | Tagum City |  | 2000000 |  | 2018-07-05 | 2019-01-15 | 100% | 1983525.71 |  | Completed as per physical accomplishment. Financial documents still on process
3. Department of Agriculture
3.1. Livestock Rehabilitation Program-Farmers hit by Typhoon Pablo |  | Provincewide |  | 7631000 |  | 09/06/2013 | 12/31/2014 | 93% | 7405434.05 |  | On going
3.2. Strengthening of Agricultural and Fishery (AFC) in DDN |  | Provincewide |  | 487500 |  | 02/01/2014 | 12/31/2017 | 81% | 407090 |  | On going
3.7. Concreting of Magupising-Cabay-angan Dujali FMR, B.E Dujali |  | Dujali |  | 18029676.06 |  | 2016-10-07 | 2017-12-31 | 80% | 9710142 |  | On going
3.8. Vermi Cast Production Facilities |  | Panabo City |  | 1500000 |  | 2017-07-03 | 2017-08-23 | 100% | 1500000 |  | COMPLETED
4. PRDP
4.1. Rehab. Of Brgy Little Panay-Katipunan-Kasilak FMR |  | Panabo City | 62092654.05 |  | 2015-09-20 |  | 2016-10-09 | 99% | 61935800.09 |  | On going |  | 1/9/19
4.2. Conc. Of New Visayas-Binancian FMR |  | Asuncion |  | 86500370.47 |  | 2015-10-18 | 2016-11-13 | 88% | 74745852.76 |  | On going | / | 1/9/19
4.4. Rehab.of Capungagan-Boundary, San Miguel FMR Kapalong |  | Kapalong |  | 108303841.7 |  | 2016-04-06 | 2020-02-14 | 93.8% | 75479834.06 |  | On-going, Increase of Project Cost due to Variation Order with Extra Work. (Php 4,992,591.29)
4.5. Rehab.of Esperanza-Poblacion Sto.Tomas FMR |  | Sto. Tomas | 117410426.3 | 117410426.3 |  | 2017-03-22 | 2019-07-22 | 87.822% | 90872722.37 |  | On-going (Waiting for approve Variation order for billing)
4.6. Rehab.of Sto. Niño Igangon FMR |  | San Isidro | 81816698.08 | 81816698.08 |  | 2016-03-21 | 2017-10-13 | 64% | 64224274.33 |  | On going
4.7. Rehab.of Pob.Limbaan-Suason-Macgum FMR |  | New Corella | 205202114.16 | 205202114.16 |  | 2016-04-08 | 2020-08-15 | 72.941% | 137812969.5 |  | Partial suspension due to soft soil
4.8. Cacao Production and Beans Marketing |  | Kapalong | 24009000 | 24009000 |  | 2017-06-15 | 2018-02-15 | 60% | 12441700 |  | On going
4.9. Construction of Dalisay Water System |  | Panabo City |  | 4664033.76 |  | 2018-01-29 | 2018-08-31 | 82.88% | 3349379.51 |  | Completed as per physical accomplishment. Financial documents still on process
4.10. Construction of Kasilak Water System |  | Panabo City |  | 7046856.27 |  | 2018-01-29 | 2018-12-05 | 87.38% | 4993322.2 |  | Completed as per physical accomplishment. Financial documents still on process
4.11 Rehab. of Sonlon-Camansa FMR Asuncion, Davao Del Norte |  | Asuncion |  | 215125015.81 |  | 2019-05-28 | 2020-12-31 | 24.41% | 71387349.72 |  | On going
4.12 Cacao Production and Beans Marketing (INFRA) |  | KAPALONG |  | 5873628.8 |  | 2019-03-19 | 2019-11-23 | 91.095% | 4698901.43 |  | Suspended due to modification of Detailed Design of mechanical Drier dated November 23, 2019
5. ACIAR
5.1. Integrated Management of Fusarium Wilt of Bananas |  | Provincewide |  | 2129512.69 |  | October 2014 | 2017 | 97% | 2123716.34
5.2. Research and Development of Integrated Crop Management for Mango |  | Provincewide |  | 4345117.19 |  | October 2014 | 2017 | 83% | 3588431.89 |  | On going
6. LGSF-CMGP
6.1. Impv't. of Maligaya- New Camiling Prov'l. Road w/ Bridge Component |  | Carmen |  | 72607552.39 |  | 2017-12-18 | 2019-07-08 | 92.65% | 72541204.84 |  | Lacking Activities to be done;Subject for liquidated damages
6.2. Road Upgrading of Anahaw- Maligaya Provincial Road |  | Carmen |  | 87202251 |  | 2017-12-24 | 2019-03-31 | 100% | 87201981 |  | 100% as of August 31, 2019 Subject for liquidated damages |  | 2457744.46 | 2019-01-17
6.3. Road Upgrading of Prk. Narafil- Barangay Site Magupising Provincial Road |  |  |  | 78228121.56 |  | 2017-03-22 | 2019-07-22 | 100% | 51973862.66 |  | Compeleted as per physical accomplishment. Financial Documents still on process
6.4. Road Upgrading of Fdr. Rd. 3 Kimamon- Luna Prov'l. Road |  | Sto. Tomas |  | 120052117 |  | 2017-12-29 | 2019-05-09 | 100% | 120052117 |  | Completed
6.5. Road Upgrading of Dagohoy- Daligdigon Prov'l. Road |  | Talaingod |  | 58048310.68 |  | 2018-01-05 | 2019-03-31 | 94.354% | 58048310.68 |  | On going
6.6. Road Upgrading of Km. 9 Sagayen- Sawata |  | San Isidro |  | 139761975.14 |  | 2018-10-01 | 2020-03-18 | 94.439% | 139761975.14 |  | Suspended dated January 28, 2019
6.7. Road Upgrading of San Vicente- Butay Provincial Road |  | Carmen |  | 19949581.18 |  | 2018-11-19 | 2019-06-08 | 100% | 19557978.88 |  | Epoxy Application & Coring
6.8. Road Upgrading of Sto.Niño-Kabankalan-LaPaz Provincial Road |  | Carmen |  | 44461624.67 |  | 2019-10-07 | 2020-05-15 | 65.03% | 27312776.03 |  | On-Going
6.9. Road Upgrading of Jct Highway-Sto. Niño-La Paz- San Vicente Provincial Rd |  | Carmen |  | 80481331.34 |  | 2019-10-07 | 2020-06-22 | 56.511% | 58152200.04 |  | On-Going
6.10. Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | Kapalong |  | 15435008 |  | 10/16/2019 | 2020-03-30 | 66.67% | 8019154.93 |  | On-Going
7. OPAPP-PAMANA
7.1. Construction of Tribal Hall, Brgy. Sto. Niño |  | Talaingod |  | 500000 |  | 2018-11-08 | 2019-01-16 | 56% | 399089.62 |  | On going
7.2. Construction of PWS Level II in Sitio Sambayon, Suaon |  | Kapalong |  | 1000000 |  | 2018-11-16 | 2019-01-24 | 100% | 828350.61 |  | Completed as per physical accomplishment. Financial documents still on process
7.3. Const. of Processing and Bagsakan Center, Palma Gil, Talaingod |  | Talaingod |  | 2500000 |  | 2019-02-02 | 2019-05-12 | 100% | 2442770.79 |  | Completed
7.4. Const. of Processing and Bagsakan Center, Brgy. Gupitan, Kapalong |  | Kapalong |  | 2500000 |  | 2018-08-29 | 2019-05-12 | 70% | 1577655.41 |  | On going
7.5. Construction of PWS Level II in Sitio Sto. Niño, Talaingod |  | Talaingod |  | 1000000 |  | 2019-02-24 | 2019-03-15 | 80% | 948011.35 |  | On going
7.6. Construction of Tribal Hall, Brgy. Gupitan, Kapalong |  | Kapalong |  | 500000 |  | 2018-11-08 | 2019-05-22 | 100% | 490433.29 |  | Completed as per physical accomplishment. Financial documents still on process
7.7. Const. of Processing and Bagsakan Center, Brgy. Sto. Niño, Talaingod |  | Talaingod |  | 2500000 |  | 2018-08-15 | 2019-05-12 | 97.27% | 2445793.77 |  | On going
7.8. Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | Kapalong |  | 2500000 |  | 2019-11-18 | 2020-04-10 | 43.76% | 1669735.58 |  | On going
7.9. Construction of PWS Level II, Prk. 1, Dagohoy, Talaingod |  | Talaingod |  | 1000000 |  | 2019-02-26 | 2019-05-18 | 100% | 947426.24 |  | Completed as per physical accomplishment. Financial documents still on process
7.10. Construction of Tribal Hall, Carmen |  | Carmen |  | 500000 |  | 2019-03-18 | 2019-05-18 | 93.21% | 451730.51 |  | On going
7.11. Construction of Tribal Hall, B.E. Dujali |  | Dujali | 500000 |  | 2019-03-21 |  | 2019-05-29 | 100% | 462214.32 |  | Completed as per physical accomplishment. Financial documents still on process
7.12 Upgrading of Existing PWS II in Sitio Langan, Gupitan, Kapalong |  | Kapalong | 2500000 |  | 2019-11-16 |  | 2020-02-27 | 74.95% | 1943457.01 |  | On going
7.13. Construction of Tribal Hall, Sto. Tomas |  | Sto. Tomas | 500000 |  | 2019-05-22 |  | 2019-07-31 | 89.5% | 435488.83 |  | Suspended 6/28/2019
7.14. Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Talaingod, Davao del Norte |  | Talaingod | 1850000 |  | 2019-07-16 |  | 2020-03-15 | 97.32% | 1696518.94 |  | On going
7.15.Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | Kapalong | 2500000 |  | 2019-03-25 |  | 2019-07-19 | 79.50% | 1505717.88 |  | On going
7.16.Rice Mill for Upland Rice,Gupitan, Kapalong |  | Kapalong | 1000000 |  | 2019-06-17 |  | - | 100% | 796590.2 |  | Completed
7.17. Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Kapalong, Davao del Norte |  | Kapalong | 1850000 |  | 2019-11-18 |  | 2020-02-26 | 80.35% | 1465350.86 |  | On Going
7.18.Rice Mill for Upland Rice,Palma Gil, Talaingod |  | Talaingod | 1000000 |  | - |  | - | 31.93% | 725308 |  | On Going
7.19.Const of Trading Post, Storage Bldg w/ 1 Unit Hauling Truck, Purok Ramihan, Datu Abdul, Panabo City, DDN |  | Panabo | 3975000 |  | 2019-11-21 |  | - | 20.51% | 3714709.28 |  | On Going
Summary:
Donor Agency |  | Downloaded |  | Obligation |  | Balance
DOH | P | 1250000 | P | 1233102.83 | P | 16897.17
PAMANA |  | 144509792.4 |  | 135764643.31 |  | 8745149.09
DA-RFU XI |  | 27648176.06 |  | 19022666.05 |  | 8625510.01
PRDP |  | 1346482877.94 |  | 601942105.97 |  | 744540771.97
ACIAR |  | 6474629.88 |  | 5712148.23 |  | 762481.65
LGSF-CMGP |  | 716227872.96 |  | 642621561.2 |  | 73606311.76
OPAPP-PAMANA |  | 30175000 |  | 24946352.49 |  | 5228647.51
TOTAL | P | 2272768349.24 |  | 1431242580.08 |  | 841525769.16
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  |  |  | WINONA J. AVENIDO, CPA, MPA |  |  |  |  | EDWIN I. JUBAHIB
|  |  |  | Provincial Accountant |  |  |  |  | Governor
Note on E17: Ging: 51,200,000.00
Note on E18: Ging: 20,000,000.00
Note on E45: Ging: 78228121.56
Note on J46: Ging: MAY expenditure
Note on J48: Ging: until may exp
Note on N12: Ging: cancelled check PROCUREMENT SERVICES-due to unavailability of stock per TFCS#300-9-17-03-1780174 dtd 03/09/2017 amounting 2,833.52
Note on N26: Ging: 15,000.00 CIP
Note on N27: Ging: 15,000.00 CIP
Note on N35: My-PC: downloaded=10,532,400.00 less: total disbursement=9,578,000.00 bal per SAAOB=954,400.00
Note on N46: Ging: per FMS= 45,201,181.68-28,708,912.96=16,492,268.72

## Sheet2
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE QUARTER ENDING SEPTEMBER 30, 2019
Province of Davao del Norte
|  | Location | Total Cost |  | Date Started |  | Target | Project Status |  | No. of | Remarks
Program or | [6 empty] | Completion | % of | Total Cost Incurred | Extensions, if | [5 empty] | apr
Project | [6 empty] | Date | Completion | to Date | any | [5 empty] | may
TRUST FUND
1. DOH-CENTER FOR HEALTH DEV'T.
1.2. Filariasis Elimination Grant |  | Province Wide |  | 1250000 |  |  |  | 95% | 1233102.83 |  | On going |  | 16897.17 |  | 1/10/19
2. PAMANA
2.1. Rehab.of San Jose Sitio Mahayahay,Magwawa FMR |  | Sto. Tomas |  | 15000000 |  | 2016-06-07 | 2017-01-04 | 98% | 13913318.99 |  | On going |  | 1086681.01 | downloadable | 1/10/19
2.3. Open.of Camansa-Sitio Bankawan-Binancian FMR |  | Asuncion |  | 20000000 |  | 2016-04-25 | 2017-01-11 | 95% | 19576395.89 |  | On going |  | 423604.11 | downloadable | 1/10/19 | 80%
2.4. Concreting/Impvt of FMR from Linayapan-Malapanit-Dangulog Ph2, Brgy Sto.Nino |  | Talaingod |  | 16050000 |  | 04/17/15 | 2016-01-15 | 95% | 16050000 |  | On going |  | 0 | downloadable | 1/10/19
2.5. Rehab/Impvt Prk 3 Palma Gil-Prk2 Tugas-Naseco FMR |  | Kapalong |  | 50500288.95 |  | 07/07/16 | 2019-04-14 | 97.76% | 48999412.68 |  | On going | / | 1500876.27 | 7998970.17 | 1/9/19
2.6. Const. of BIGA RCDG Bridges |  | Kapalong |  | 24959503.45 |  | 07/01/16 | 2019-09-27 | 68.97% | 20000000 |  | On going | / | 4959503.45 | 16256074.48 | 1/9/19
2.7. Opening/Impvt Mambing Brgy Cabidianan FMR |  | New Corella |  | 10000000 |  | 2016-03-15 | 2016-09-02 | 95% | 9328117.06 |  | On going |  | 671882.94 | 2nd tranche 4/06/2018 | 1/9/19
2.8.Construction of Food Grade Banana Flour Production Facility |  | Panabo City |  | 3000000 |  | 2017-07-03 | 2017-09-23 | 100% | 3000000 |  | COMPLETED |  | 0 |  | 1/10/19
2.9. Construction of Civic Center, Madaum |  | Tagum City |  | 3000000 |  | 2018-01-28 | 2018-09-24 | 100% | 2913872.98 |  | Completed as per physical accomplishment. Financial documents still on process |  | 86127.02 |  | 1/10/19
2.10. Construction of Civic Center, San Isidro |  | Tagum City |  | 2000000 |  | 2018-07-05 | 2019-01-15 | 100% | 1600000 |  | Completed as per physical accomplishment. Financial documents still on process |  | 400000
3. Department of Agriculture
3.1. Livestock Rehabilitation Program-Farmers hit by Tyhoon Pablo |  | Provincewide |  | 7631000 |  | 09/06/2013 | 12/31/2014 | 93% | 7405434.05 |  | On going |  | 225565.95 |  | 10/02/2018
3.2. Strengthening of Agricultural and Fishery (AFC) in DDN |  | Provincewide |  | 487500 |  | 02/01/2014 | 12/31/2017 | 81% | 377500 |  | On going |  | 110000 |  | 10/02/2018
3.7. Concreting of Magupising-Cabay-angan Dujali FMR, B.E Dujali |  | Dujali |  | 18029676.06 |  | 2016-10-07 | 2017-12-31 | 80% | 9710142 |  | On going |  | 8319534.06 | zero | 10/02/2018
3.8. Vermi Cast Production Facilities |  | Panabo City |  | 1500000 |  | 2017-07-03 | 2017-08-23 | 100% | 1500000 |  | COMPLETED |  | 0 |  | 10/02/2018
4. PRDP
4.1. Rehab. Of Brgy Little Panay-Katipunan-Kasilak FMR |  | Panabo City | 62092654.05 |  | 2015-09-20 |  | 2016-10-09 | 99% | 61935800.09 |  | On going |  | 156853.96 | per saaob march18=156,853.96 |  | 1/9/19
4.2. Conc. Of New Visayas-Binancian FMR |  | Asuncion |  | 86500370.47 |  | 2015-10-18 | 2016-11-13 | 88% | 74745852.76 |  | On going | / | 11754517.71 | per saaob DEC18=819,447.32 |  | 1/9/19
4.4. Rehab.of Capungagan-Boundary, San Miguel FMR Kapalong |  | Kapalong |  | 108303841.7 |  | 2016-04-06 | 2019-08-28 | 85.15% | 48000030.83 |  | On going |  | 60303810.87 | 1/9/19 | increase project cost
4.5. Rehab.of Esperanza-Poblacion Sto.Tomas FMR |  | Sto. Tomas | 117410426.3 | 117410426.3 |  | 2017-03-22 | 2019-07-22 | 89.821% | 90872722.37 |  | On-going - time extension on process |  |  | 1/9/19
4.6. Rehab.of Sto. Niño Igangon FMR |  | San Isidro | 81816698.08 | 81816698.08 |  | 2016-03-21 | 2017-10-13 | 64% | 64224274.33 |  | On going |  | 17592423.75 | 1/9/19
4.7. Rehab.of Pob.Limbaan-Suason-Macgum FMR |  | New Corella | 205202114.16 | 205202114.16 |  | 2016-04-08 | 2020-06-14 | 65.657% | 104104512.35 |  | On going |  | increase project cost | 1/9/19
4.8. Cacao Production and Beans Marketing |  | Kapalong | 24009000 | 24009000 |  | 2017-06-15 | 2018-02-15 | 60% | 12441700 |  | On going |  | 11567300 | 954400 | 1/11/19
4.9. Construction of Dalisay Water System |  | Panabo City |  | 4664033.76 |  | 2018-01-29 | 2018-08-31 | 82.88% | 3513773.78 |  | Suspended dated 08/17/18 -Physically completed. However, due to delay in the release of funds from the PRDP, the contractor was not able to….
4.10. Construction of Kasilak Water System |  | Panabo City |  | 7046856.27 |  | 2018-01-29 | 2018-12-05 | 87.38% | 4993322.2 |  | Suspended dated 11/17/18 -Physically completed. However, due to delay in the release of funds from the PRDP, the contractor was not able to….
5. ACIAR
5.1. Integrated Management of Fusarium Wilt of Bananas |  | Provincewide |  | 2129512.69 |  | October 2014 | 2017 | 97% | 2123716.34
5.2. Research and Development of Integrated Crop Management for Mango |  | Provincewide |  | 4345117.19 |  | October 2014 | 2017 | 83% | 3504758.15 |  | On going |  | 840359.04 | 1/11/19
6. LGSF-CMGP
6.1. Impv't. of Maligaya- New Camiling Prov'l. Road w/ Bridge Component |  | Carmen |  | 72607552.39 |  | 2017-12-18 | 2019-07-08 | 92.65% | 68687488.45 |  | Subject for liquidated damages
6.2. Road Upgrading of Anahaw- Maligaya Provincial Road |  | Carmen |  | 87202251 |  | 2017-12-24 | 2019-03-31 | 100% | 85940944.66 |  | 100% as of August 31, 2019 Subject for liquidated damages |  | 1261306.34 | 1/11/19 | 85% | 2457744.46 | 2019-01-17
6.3. Road Upgrading of Prk. Narafil- Barangay Site Magupising Provincial Road |  |  |  | 78228121.56 |  | 2017-03-22 | 2019-07-22 | 100% | 51973862.66 |  | Compeleted as per physical accomplishment. Financial Documents still on process |  | 37488062.29 | 1/9/19
6.4. Road Upgrading of Fdr. Rd. 3 Kimamon- Luna Prov'l. Road |  | Sto. Tomas |  | 120052117 |  | 2017-12-29 | 2019-05-09 | 100% | 120052117 |  | Completed |  | 0 | 1/9/19
6.5. Road Upgrading of Dagohoy- Daligdigon Prov'l. Road |  | Talaingod |  | 58048310.68 |  | 2018-01-05 | 2019-03-31 | 94.354% | 58048310.68 |  | On going |  | 0 | 01/09/19
6.6. Road Upgrading of Km. 9 Sagayen- Sawata |  | San Isidro |  | 139761975.14 |  | 2018-10-01 | 2019-08-22 | 88.32% | 119359831.58 |  | On going |  | 20402143.56
6.7. Road Upgrading of San Vicente- Butay Provincial Road |  |  |  | 19949581.18 |  | 2018-11-19 | 2019-06-08 | 100% | 15471254.93 |  | Epoxy Application & Coring |  | 4478326.25 | FMS=20M
7. OPAPP-PAMANA
7.1. Construction of Tribal Hall, Brgy. Sto. Niño |  | Talaingod |  | 500000 |  | 2018-11-08 | 2019-01-16 | 56% | 399089.62 |  | On going |  | 100910.38
7.2. Construction of PWS Level II in Sitio Sambayon, Suaon |  | Kapalong |  | 1000000 |  | 2018-11-16 | 2019-01-24 | 100% | 828350.61 |  | Completed as per physical accomplishment. Financial documents still on process |  | 40631.25
7.3. Const. of Processing and Bagsakan Center, Palma Gil, Talaingod |  | Talaingod |  | 2500000 |  | 2019-02-02 | 2019-05-12 | 100% | 1918166.5 |  | On going |  | 581833.5
7.4. Const. of Processing and Bagsakan Center, Brgy. Gupitan, Kapalong |  | Kapalong |  | 2500000 |  | 2018-08-29 | 2019-05-12 | 70% | 1489896.41 |  | On going |  | 1010103.59
7.5. Construction of PWS Level II in Sitio Sto. Niño, Talaingod |  | Talaingod |  | 1000000 |  | 2019-02-24 | 2019-03-15 | 80% | 797923.41 |  | On going |  | 202076.59
7.6. Construction of Tribal Hall, Brgy. Gupitan, Kapalong |  | Kapalong |  | 500000 |  | 2018-11-08 | 2019-05-22 | 100% | 490433.29 |  | Completed as per physical accomplishment. Financial documents still on process |  | 9566.71
7.7. Const. of Processing and Bagsakan Center, Brgy. Sto. Niño, Talaingod |  | Talaingod |  | 2500000 |  | 2018-08-15 | 2019-05-12 | 97.27% | 2352452.77 |  | On going |  | 147547.23
7.8. Const. of Processing and Bagsakan Center, Brgy. Gupitan, Kapalong |  | Kapalong |  | 2500000 |  | 2018-08-29 | 2019-05-12 | 100% | 1489896.41 |  | Completed as per physical accomplishment. Financial documents still on process |  | 1010103.59
7.9. Construction of PWS Level II, Prk. 1, Dagohoy, Talaingod |  | Talaingod |  | 1000000 |  | 2019-02-26 | 2019-05-18 | 100% | 947426.24 |  | Completed as per physical accomplishment. Financial documents still on process |  | 52573.76
7.10. Construction of Tribal Hall, Carmen |  | Carmen |  | 500000 |  | 2019-03-18 | 2019-05-18 | 93.21% | 462250.51 |  | On going |  | 37749.49
7.11. Construction of Tribal Hall, B.E. Dujali |  | Dujali | 500000 |  | 2019-03-21 |  | 2019-05-29 | 100% | 472734.32 |  | Completed as per physical accomplishment. Financial documents still on process |  | 27265.68
7.12 Upgrading of Existing PWS II in Sitio Langan, Gupitan, Kapalong |  | Kapalong | 2500000 |  | 2019-03-25 |  | 2019-09-19 | 48% | 1142677.54 |  | On going |  | 1357322.46
7.13. Construction of Tribal Hall, Sto. Tomas |  | Sto. Tomas | 500000 |  | - |  | - | 89.5% | 435488.83 |  | Suspended 6/28/2019 Suspende due to the delivery of materials J.O. |  | 64511.17
7.14. Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Talaingod, Davao del Norte |  | Talaingod | 1850000 |  | 2019-07-16 |  | 2019-11-13 | 34.47% | 236460.96 |  | On going |  | 1613539.04
7.15.Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | Kapalong | 2500000 |  | 2019-03-25 |  | 2019-07-19 | 79.50% | 1354360.28 |  | On going |  | 1145639.72
7.16.Rice Mill for Upland Rice,Gupitan, Kapalong |  | Kapalong | 1000000 |  | 2019-06-17 |  | - | 100% | 785066.13 |  | Completed |  | 214933.87
Summary:
Donor Agency |  | Downloaded |  | Obligation |  | Balance
DOH | P | 1250000 | P | 1233102.83 | P | 16897.17
PAMANA |  | 144509792.4 |  | 135381117.6 |  | 9128674.8
DA-RFU XI |  | 27648176.06 |  | 18993076.05 |  | 8655100.01
PRDP |  | 1125484233.33 |  | 464831988.71 |  | 660652244.62
ACIAR |  | 6474629.88 |  | 5628474.49 |  | 846155.39
LGSF-CMGP |  | 575849908.95 |  | 519533809.96 |  | 56316098.99
OPAPP-PAMANA |  | 23350000 |  | 15602673.83 |  | 7747326.17
TOTAL | P | 1904566740.62 |  | 1161204243.47 |  | 743362497.15
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
WINONA J. AVENIDO, CPA, MPA |  |  |  | EDWIN I. JUBAHIB
Provincial Accountant |  |  |  | Governor
Note on E17: Ging: 51,200,000.00
Note on E18: Ging: 20,000,000.00
Note on E43: Ging: 78228121.56
Note on J44: Ging: MAY expenditure
Note on J46: Ging: until may exp
Note on N12: Ging: cancelled check PROCUREMENT SERVICES-due to unavailability of stock per TFCS#300-9-17-03-1780174 dtd 03/09/2017 amounting 2,833.52
Note on N26: Ging: 15,000.00 CIP
Note on N27: Ging: 15,000.00 CIP
Note on N35: My-PC: downloaded=10,532,400.00 less: total disbursement=9,578,000.00 bal per SAAOB=954,400.00
Note on N44: Ging: per FMS= 45,201,181.68-28,708,912.96=16,492,268.72